## Slide 1: Project proposal
Biomedical Image Analysis

## Slide 2: Data keine sorge nur mal ein grober überblick pink bleibt nicht…. :P
3 Datasets
N2DH- GOWT1
N2DL-HeLa
NIH3T3
Why Otsu thresholding?
Würde irgenwie ziemlich am anfang erklären warum wir jetzt otsu verwinden und was das genau bringt für unsere bilder. Evtl 2 sätze dazu quasi als einleitungssatz? Und dann sagen genaueres kommt später oder sowas meint ihr?

## Slide 3: N2DH- GOWT1 GFP transfected GOWT1 mouse embryonic stem cells
6 images total
1024x1024 pixels
10-20 nulei per image
Challenge:
…..
Hier müsste ein histogramm sein..
(in arbeit)

## Slide 4: NIH3T3 Mouse embryonic cells stained with Hoechst
18 images total
Size: 1344x1024 pixels
about 60 nuclei per image
Challenge:
…..
Bild und histogramm

## Slide 5: N2DL-HeLa HeLa cells stably expressing H2b-GFP
4 images total
Size: 1100x 700 pixels
30-50 nuclei per image
Challenge:
….
Bild und histogramm

## Slide 6: Local Thresholding - Sliding window scheme

## Slide 7: Otsu Thresholding

## Slide 8: Dice Score Coefficient
Kurzerklaerung was TP, FP usw ist also
gt = ground truth; pt = post tresholding
TP : Both pixels white
FP : gt pixel black, pt pixel white
TN : both pixels black
FN : gt pixel white, pt pixel black
Tresholding using online tool
( imageonline.co)
Ground truth picture

## Slide 9: Eulers rings normal version and dice score #muss noch ueberlegen wie genau ich es mache also in what order

## Slide 10: wie sieht es statistisch auss (eulers rings)
Hier perfect scenario aka ueberlappende eulers rings
Realistic scenario
FN=0
FP=0
DSC= 2TP/2TP = 1
+ kurzerklaerung wie es zu dsc=0 kommen wurde
FN>0
FP>0
DSC=2TP/(2TP+FN+FP)
  TP = True positives
  FP = False positives
  FN = False negatives

## Slide 11: Timeline
10.05.
17.05.
31.05.
07.06.
14.06.
21.06.
28.06.
First steps
Project proposal
Alternative evaluation methods and further ideas
Local threshold
Preprocessing and testing
Otsu and Dice
Cell counting
Buffer and report
Final presentation

## Slide 12: Milestones and Deliverables
First steps
Plan and organize team
Read resources and understand data
Propject proposal
Visualize data and understand algorithms
Main algorithms
Implement Otsu thresholding and dice score
Finish project proposal
Test it on data

## Slide 13: Milestones and Deliverables
Preprocessing and testing
Implement different preprocessing features
Test pipeline on optimized images
Local threshold
Impement sliding window scheme
Organize and optimize code
Alternative evaluation methods and further ideas
Implement further evaluation methods
Implement two-level-Otsu
Cell counting
Implement cell counting algorithm
Buffer and Final presentation
Compare/collaborate with other team
Clean GitHub and write final report

## Slide 14: Team
Meetings
Teamwork
GitHub
2x a week
Live and online
Work in pairs
Help each other
Use project feature
Strucuture repository